## Jira-allfiles
Task Summary | Sprint | Assignee | Issue Type | Status | Project key | Project name | Project lead | Resolution | Reporter | Created | Resolved | Status Category
Delete account by manager API | Sprint 6 | Anushree Ganta | Story | Done | CMPE202 | Group-15 | Ealrada Piroyan | Done | Anushree Ganta | 2021-05-09 03:02 | 2021-05-12 16:47 | Done
EC2 instance Deployment | Sprint 6 | Zeel Jayeshkumar | Story | Done | CMPE202 | Group-15 | Ealrada Piroyan | Done | Anushree Ganta | 2021-05-05 06:59 | 2021-05-12 00:42 | Done
Bill Payments UI | Sprint 6 | Anagha Sethuraman | Story | Done | CMPE202 | Group-15 | Ealrada Piroyan | Done | Anushree Ganta | 2021-05-05 06:59 | 2021-05-12 13:57 | Done
Authorization | Sprint 6 | Anushree Ganta | Story | Done | CMPE202 | Group-15 | Ealrada Piroyan | Done | Anushree Ganta | 2021-05-05 06:58 | 2021-05-08 06:16 | Done
Completing Transfer API (Back-End) | Sprint 6 | Ealrada Piroyan | Story | Done | CMPE202 | Group-15 | Ealrada Piroyan | Done | Anushree Ganta | 2021-05-05 06:57 | 2021-05-11 22:28 | Done
Apply load balancer | Sprint 6 | Zeel Jayeshkumar | Story | Done | CMPE202 | Group-15 | Ealrada Piroyan | Done | Anushree Ganta | 2021-05-05 06:59 | 2021-05-12 00:42 | Done
Completing Register API (Back-End) | Sprint 6 | Ealrada Piroyan | Story | Done | CMPE202 | Group-15 | Ealrada Piroyan | Done | Anushree Ganta | 2021-05-05 06:57 | 2021-05-11 20:28 | Done
Final testing and host app on AWS | Sprint 6 | Sandhya Santhanam | Story | Done | CMPE202 | Group-15 | Ealrada Piroyan | Done | Anushree Ganta | 2021-05-05 06:57 | 2021-05-12 14:10 | Done
Autopay(One time-time intervals) | Sprint 5 | Anushree Ganta | Story | Done | CMPE202 | Group-15 | Ealrada Piroyan | Done | Anagha Sethuraman | 2021-04-28 22:14 | 2021-05-05 06:53 | Done
Refund Database(Transactions) | Sprint 5 | Anushree Ganta | Story | Done | CMPE202 | Group-15 | Ealrada Piroyan | Done | Anagha Sethuraman | 2021-04-28 22:14 | 2021-05-05 06:53 | Done
View/Search Transactions | Sprint 5 | Zeel Jayeshkumar | Story | Done | CMPE202 | Group-15 | Ealrada Piroyan | Done | Anagha Sethuraman | 2021-04-28 22:08 | 2021-05-05 02:03 | Done
Internal Transfer UI | Sprint 5 | Anagha Sethuraman | Story | Done | CMPE202 | Group-15 | Ealrada Piroyan | Done | Anagha Sethuraman | 2021-04-28 22:14 | 2021-05-05 06:53 | Done
Completing withdraw REST API | Sprint 5 | Ealrada Piroyan | Story | Done | CMPE202 | Group-15 | Ealrada Piroyan | Done | Ealrada Piroyan | 2021-04-28 22:14 | 2021-05-03 21:15 | Done
Start working on Transfer REST API | Sprint 5 | Ealrada Piroyan | Story | Done | CMPE202 | Group-15 | Ealrada Piroyan | Done | Ealrada Piroyan | 2021-04-28 22:14 | 2021-05-03 21:14 | Done
Create blueprints for different APIs | Sprint 5 | Sandhya Santhanam | Story | Done | CMPE202 | Group-15 | Ealrada Piroyan | Done | Anagha Sethuraman | 2021-04-28 22:13 | 2021-05-04 19:26 | Done
Integration of front-end to backend | Sprint 5 | Zeel Jayeshkumar | Story | Done | CMPE202 | Group-15 | Ealrada Piroyan | Done | Anagha Sethuraman | 2021-04-28 22:08 | 2021-05-05 02:03 | Done
Refund Page | Sprint 5 | Anagha Sethuraman | Story | Done | CMPE202 | Group-15 | Ealrada Piroyan | Done | Anagha Sethuraman | 2021-04-28 22:08 | 2021-05-05 06:53 | Done
Learning more avanced FLASK skills | Sprint 4 | Ealrada Piroyan | Story | Done | CMPE202 | Group-15 | Ealrada Piroyan | Done | Ealrada Piroyan | 2021-04-21 21:51 | 2021-04-28 21:41 | Done
BackEnd-Add Account by manager | Sprint 4 | Anushree Ganta | Story | Done | CMPE202 | Group-15 | Ealrada Piroyan | Done | Ealrada Piroyan | 2021-04-21 21:50 | 2021-04-26 19:40 | Done
Close Account by manager | Sprint 4 | Anushree Ganta | Story | Done | CMPE202 | Group-15 | Ealrada Piroyan | Done | Ealrada Piroyan | 2021-04-21 21:50 | 2021-04-26 19:40 | Done
Close Account by manager UI | Sprint 4 | Zeel Jayeshkumar | Story | Done | CMPE202 | Group-15 | Ealrada Piroyan | Done | Anagha Sethuraman | 2021-04-21 21:49 | 2021-04-26 19:40 | Done
Deposit Validations | Sprint 4 | Anagha Sethuraman | Story | Done | CMPE202 | Group-15 | Ealrada Piroyan | Done | Anagha Sethuraman | 2021-04-21 21:49 | 2021-04-26 19:40 | Done
Learn Flask(Advance) | Sprint 4 | Sandhya Santhanam | Story | Done | CMPE202 | Group-15 | Ealrada Piroyan | Done | Ealrada Piroyan | 2021-04-21 21:48 | 2021-04-27 18:19 | Done
Deposit API | Sprint 4 | Sandhya Santhanam | Story | Done | CMPE202 | Group-15 | Ealrada Piroyan | Done | Ealrada Piroyan | 2021-04-19 22:13 | 2021-04-28 20:40 | Done
Start working on Withdraw REST API | Sprint 4 | Ealrada Piroyan | Story | Done | CMPE202 | Group-15 | Ealrada Piroyan | Done | Ealrada Piroyan | 2021-04-19 22:13 | 2021-04-26 19:40 | Done
Deposit UI | Sprint 4 | Anagha Sethuraman | Story | Done | CMPE202 | Group-15 | Ealrada Piroyan | Done | Ealrada Piroyan | 2021-04-19 22:12 | 2021-04-28 21:40 | Done
Overview Page for Manager | Sprint 4 | Zeel Jayeshkumar | Story | Done | CMPE202 | Group-15 | Ealrada Piroyan | Done | Ealrada Piroyan | 2021-04-19 22:12 | 2021-04-28 15:02 | Done
Integration of Login/Add Client to UI | Sprint 3 | Zeel Jayeshkumar | Story | Done | CMPE202 | Group-15 | Ealrada Piroyan | Done | Anagha Sethuraman | 2021-04-16 22:51 | 2021-04-19 22:08 | Done
Role based authentication | Sprint 3 | Anagha Sethuraman | Story | Done | CMPE202 | Group-15 | Ealrada Piroyan | Done | Anagha Sethuraman | 2021-04-16 22:50 | 2021-04-19 22:08 | Done
SearchAPI | Sprint 3 | Anushree Ganta | Story | Done | CMPE202 | Group-15 | Ealrada Piroyan | Done | Ealrada Piroyan | 2021-04-16 22:43 | 2021-04-21 12:13 | Done
FrontEnd-Add/Close Account | Sprint 3 | Anushree Ganta | Story | Done | CMPE202 | Group-15 | Ealrada Piroyan | Done | Ealrada Piroyan | 2021-04-16 22:43 | 2021-04-21 12:13 | Done
Add Account UI | Sprint 3 | Zeel Jayeshkumar | Story | Done | CMPE202 | Group-15 | Ealrada Piroyan | Done | Ealrada Piroyan | 2021-04-16 22:40 | 2021-04-27 18:19 | Done
Learning more advanced skills on FLASK API | Sprint 3 | Ealrada Piroyan | Story | Done | CMPE202 | Group-15 | Ealrada Piroyan | Done | Ealrada Piroyan | 2021-04-16 22:29 | 2021-04-21 20:56 | Done
Start working on UML diagram | Sprint 3 | Anushree Ganta | Story | Done | CMPE202 | Group-15 | Ealrada Piroyan | Done | Ealrada Piroyan | 2021-04-16 22:05 | 2021-04-21 20:56 | Done
Learning-Flask and work on Login API | Sprint 3 | Sandhya Santhanam | Story | Done | CMPE202 | Group-15 | Ealrada Piroyan | Done | Ealrada Piroyan | 2021-04-16 22:03 | 2021-04-19 22:08 | Done
Profile Settings | Sprint 3 | Anagha Sethuraman | Story | Done | CMPE202 | Group-15 | Ealrada Piroyan | Done | Ealrada Piroyan | 2021-04-16 22:03 | 2021-04-19 12:15 | Done
Start working on Register REST API | Sprint 3 | Ealrada Piroyan | Story | Done | CMPE202 | Group-15 | Ealrada Piroyan | Done | Ealrada Piroyan | 2021-04-16 22:02 | 2021-04-17 19:06 | Done
Login Page-Client/Manager , | Sprint 2 | Anagha Sethuraman | Story | Done | CMPE202 | Group-15 | Ealrada Piroyan | Done | Sandhya Santhanam | 2021-04-07 22:08 | 2021-04-16 21:58 | Done
Add Client -Registration UI | Sprint 2 | Zeel Jayeshkumar | Story | Done | CMPE202 | Group-15 | Ealrada Piroyan | Done | Zeel Jayeshkumar | 2021-04-05 20:39 | 2021-04-16 21:58 | Done
Learning MongoDB | Sprint 2 | Anushree Ganta | Story | Done | CMPE202 | Group-15 | Ealrada Piroyan | Done | Ealrada Piroyan | 2021-04-05 20:34 | 2021-04-16 21:58 | Done
Learning how to create REST APIs in Flask | Sprint 2 | Ealrada Piroyan | Story | Done | CMPE202 | Group-15 | Ealrada Piroyan | Done | Ealrada Piroyan | 2021-04-05 20:30 | 2021-04-16 21:30 | Done
Creating UI Wireframes | Sprint 2 | Ealrada Piroyan | Story | Done | CMPE202 | Group-15 | Ealrada Piroyan | Done | Ealrada Piroyan | 2021-04-05 20:30 | 2021-04-16 23:30 | Done
Identifying Components | Sprint 2 | Zeel Jayeshkumar | Story | Done | CMPE202 | Group-15 | Ealrada Piroyan | Done | Ealrada Piroyan | 2021-04-05 20:27 | 2021-04-16 21:58 | Done
Architectural Diagram | Sprint 2 | Anagha Sethuraman | Story | Done | CMPE202 | Group-15 | Ealrada Piroyan | Done | Ealrada Piroyan | 2021-04-05 20:26 | 2021-04-16 21:58 | Done
Working on HomePage UI layout | Sprint 2 | Anushree Ganta | Story | Done | CMPE202 | Group-15 | Ealrada Piroyan | Done | Ealrada Piroyan | 2021-04-05 20:23 | 2021-04-16 21:59 | Done
Create deployment diagram | Sprint 2 | Sandhya Santhanam | Story | Done | CMPE202 | Group-15 | Ealrada Piroyan | Done | Ealrada Piroyan | 2021-04-05 20:20 | 2021-04-16 21:59 | Done
Research on various technologies | Sprint 1 | All | Story | Done | CMPE202 | Group-15 | Ealrada Piroyan | Done | Ealrada Piroyan | 2021-03-31 | 2021-04-05 20:20 | Done
brain storming about flow, aspect and technologies. | Sprint 1 | All | Story | Done | CMPE202 | Group-15 | Ealrada Piroyan | Done | Ealrada Piroyan | 2021-03-31 | 2021-04-05 20:20 | Done